## All
M.S.N | PROJECT NUMBER | PROJECT CATEGORY | Product Catogory | Title of Project | Scope Of Development | Business Unit | Market Segment | Customer Name | Enquiry Number | Project Risk Classification | Engineering Leader (Old Project Owner) | Business Opportunity | PROJECT OWNER | DATE OF START | TARGET DATE | Project Phase | Forecast Completion Date | Actual Start Date | Actual Completion date | Overall Status | Major/ Customer Specific | Status
1 | 1920CERT01 | Product Certification | Certification | AAR Certification | System Certification | bu #1 | Oil & Gas |  | NA | Minor Change | Vinod Ghatge | Silver | Ramalal | When Needed | - | Phase 4 - Validation |  |  |  | Killed | Major | On Hold
2 | 2122CERT01 | Product Certification | Certification | NADCAP For Aerospace Fittings | System Certification | bu #2 | Oil & Gas | Aerospace | NA | Minor Change | Praveen Patil | Silver | Ramalal | 2021-12-01 | - | Phase 1 - Definition |  |  |  | Killed | Major | Completed
3 | 1920SERVICES02 | Process Development | Services | Skids (pharma, Tube Bending, Pre Engineered Assemblies) | As & when needed | bu #1 | Aerospace | NA | NA | Complete New Product | Krishna Rashtrakut | Gold | Nitin | When Needed | - | Phase 0 |  |  |  | Killed | Customer Specific | On Demand- Quotation send customer
4 | 1920SERVICES03 | Process Development | Services | Air Reservoir- Medha Servo | As & when needed | bu #2 | Aerospace |  | NA | Complete New Product | Vinod Ghatge | Gold | Nitin Patil | 2023-02-13 | 2024-09-30 | Phase 5 - Production |  |  |  | In-Process | Customer Specific | Feasibility Study Done- Quotation submitted to customer
5 | 1920VLAVE20 | Process Development | Services | Railway Break Stand Manifold- BEML | Study of Air distribution valve/ Re- engineering of ADV Study of E70 and CCB break system and develop all related component with supplier TOPGRIP, ACCURATE- Pressure switch | bu #1 | Aerospace |  | NA | Minor Change | Krishna Rashtrakut | Diamond | Santosh K, Abhay Dhake, Dilip | When Needed | - | Phase 4 - Validation |  |  |  | Killed | Customer Specific | On going- Dismenteling done.
6 | 1920SERVICES07 | Process Development | Services | Industries 4.0- PLM (Design Data Systematic Organise i.e. Drawing, Technical Spec & Keep updating through Software) | Review For Assembly & Inspection and as needed | bu #2 | Aerospace | NA | NA | Complete New Product | Praveen Patil | Silver | Rahul P./Sanket | 2021-07-23 | 2024-09-30 | Phase 1 - Definition |  |  |  | In-Process | Major | Ongoing : Team Centre, Solid works Library Software's evaluation is progressively going on- Trail-review- discussion. System order placed.
7 | 1920FITTINGE01 | Test Stand Development | Fittings | Forging Development for Double ferrule. 350 Nos of drawings for forgings- Now its is almost 700+ Items code | As needed | bu #1 | Semi-Conductor | NA | NA | Minor Change | Vinod Ghatge | Gold | Krishna | When Needed | - | Phase 4 - Validation |  |  |  | Killed | Major | On Demand- Optimisation design for Cost Saving & reduce no of parts.
8 | 1920FITTINGE02 | Test Stand Development | Fittings | JIC fittings/DIN 8434 | Section 5 Out of which We need to develop as & when needed as per customer -All sections- Series to be provided for all types of fittings | bu #2 | Semi-Conductor | NA | NA | Minor Change | Vinod Ghatge | Silver | Pravin P | 2021-07-31 | 2024-09-30 | Phase 2 - Concept development |  |  |  | On-Hold | Major | Ongoing for 1) Flared Type 24 Deg. For Domestic Customer 2) Flared Type 37 Deg.
9 | 1920FITTINGE03 | Test Stand Development | Fittings | Design And development of Double ferrule fittings for RM: 6Mo and Inconel, Super Duplex | Test Validation as per existing drag & pressure calculation for tubing. | bu #1 | Semi-Conductor | NA | NA | Complete New Product | Praveen Patil | Diamond | Krishna | 2021-07-31 | - | Phase 3 - Detail design |  |  |  | On-Hold | Major | Completed
10 | 1920FITTINGE04 | Test Stand Development | Fittings | Fittings EO2 Bonded Type | Under uaidation 6 MM to 42 in L 12,18,28,22 Sample is ready & validated, Sereis S -16MM taken for validation | bu #2 | Semi-Conductor |  | NA | Minor Change | Krishna Rashtrakut | Platinum | Nitin Patil | 2021-03-01 | 2024-09-30 | Phase 3 - Detail design |  |  |  | In-Process | Major | Ongoing- L Sereis Drawings Ready To do Burst Test for Validation (tube size 6,8,12 mm completed) 18 mm in process
11 | 1920FITTINGE05 | Test Stand Development | Fittings | DFF remapping- Our Product Performance with Swagelok & Parker Latest Series. Size 16 & Size 12 | Testing for Burst and then revalidate | bu #1 | Semi-Conductor | NA | NA | Minor Change | Praveen Patil | Platinum | Pravin P | When Needed | - | Phase 1 - Definition |  |  |  | Killed | Major | On going, Concetraded on size 1/4 Inch CNG Fittings
12 | 1920FITTINGE06 | Test Stand Development | Fittings | CPI remapping - F1387 | Validation Trial & Certification | bu #2 | Semi-Conductor | NA | NA | Major Change | Krishna Rashtrakut | Gold | Krishna | When Needed | - | Phase 4 - Validation |  |  |  | On-Hold | Major | On Hold- No requirment
13 | 1920FITTINGE07 | Test Stand Development | Fittings | Flex grip | As per Customer Requirment -Size -8MM to 44.5 MM OD size. (Pipe Or Tube) | bu #1 | Semi-Conductor |  | NA | Complete New Product | Nitin Patil | Gold | Pravin P | 2020-12-18 | 2024-09-30 | Phase 1 - Definition |  |  |  | Killed | Major | Ongoing-Drawing Ready - Quotation stage, Validation Trail completed
14 | 1920FITTINGE08 | Product Certification | Certification | Cryogenic fittings CAE validation | Certification of Cryogenic for fittings | bu #2 | Oil & Gas | NA | NA | Major Change | Krishna Rashtrakut | Silver | Not Assigned | When Needed | - | Phase 0 |  |  |  | In-Process | Customer Specific | On Hold
15 | 1920FITTINGE09 | Test Stand Development | Fittings | Aluminium fittings as BI Forging -JIC Type.-Aerospace Fittings | Product Development | bu #1 | Semi-Conductor |  | NA | Major Change | Nitin Patil | Diamond | Pravin P | 2022-04-01 | 2023-12-31 | Phase 5 - Production |  |  |  | Killed | Major | Done- JJG ,AZAD
16 | 1920FITTINGE10 | Test Stand Development | Fittings | Air Brake Fittings - NTA | O live ferrules Series | bu #2 | Semi-Conductor |  | NA | Complete New Product | Praveen Patil | Bronze | Krishna | When Needed | - | Phase 2 - Concept development |  |  |  | Killed | Major | Ongoing- 2 Sizes Developed Balance (5 Sizes) to Review.
17 | 1920FITTINGE11 | Test Stand Development | Fittings | O ring Face Seal fittings- ORFS. Tube Flare/Not flare | Drg. Made Need validation | bu #2 | Semi-Conductor |  | NA | Major Change | Praveen Patil | Platinum | Pravin P | When Needed | - | Phase 4 - Validation |  |  |  | Killed | Major | Ongoing- As per BEML Design Done, Validation is on Hold
18 | 1920FITTINGE12 | Test Stand Development | Fittings | Hose Fittings- 6 sections | 5 Validated & Balance under development | bu #1 | Semi-Conductor |  | NA | Minor Change | Vinod Ghatge | Diamond | Nitin | 2021-07-01 | 2023-09-30 | Phase 0 |  |  |  | On-Hold | Major | Done
19 | 1920FITTINGE13 | Test Stand Development | Fittings | 60° Cone Connectors- DIN 8434-6 | Drg. Made Need validation | bu #2 | Semi-Conductor |  | NA | Minor Change | Nitin Patil | Silver | Krishna | 2021-07-01 | 2025-03-30 | Phase 5 - Production |  |  |  | In-Process | Customer Specific | Ongoing- Design to be approve By GE- Design completed for 2 sizes and validation cpmleted
20 | 1920FITTINGE14 | Test Stand Development | Fittings | GE Fittings (Out of 412-270 Possible to developed) | FAI & Overall | bu #1 | Semi-Conductor |  | NA | Minor Change | Vinod Ghatge | Gold | Pravin P | 2021-05-28 | 2023-09-30 | Phase 3 - Detail design |  |  |  | In-Process | Major | Done
21 | 1920FITTINGE15 | Test Stand Development | Fittings | Hardware's for Railways | Nut Bolts as per RDSO Specification0- TO Buy & Trade. | bu #2 | Semi-Conductor |  | NA | Complete New Product | Nitin Patil | Gold | Not Assigned | When Needed | - | Phase 0 |  |  |  | In-Process | Customer Specific | As & When Needed
22 | 1920FITTINGE16 | Test Stand Development | Fittings | Pharma Fitting/Ultra pure fittings, ISO 2037 | Oxy clean Certification For Fittings | bu #1 | Semi-Conductor | NA | NA | Major Change | Nitin Patil | Bronze | Not Assigned | When Needed | - | Phase 0 |  |  |  | Killed | Customer Specific | As & When Needed
23 | 1920FITTINGE17 | Test Stand Development | Fittings | Dielectric fittings | Need to See the details- Competitors Products vs Our scope | bu #2 | Semi-Conductor | NA | NA | Complete New Product | Krishna Rashtrakut | Platinum | Krishna/Rahul P. | When Needed | - | Phase 4 - Validation |  |  |  | On-Hold | Customer Specific | On-Hold
24 | 1920FITTINGE18 | Test Stand Development | Fittings | High Pressure Fittings above 10,000 PSI HIP or Butec 60,000 PSI | Need to See the details- Competitors Products vs Our scope to define. HIP, Butec | bu #1 | Semi-Conductor | NA | NA | Major Change | Vinod Ghatge | Platinum | Krishna | 2019-12-01 | 2025-03-20 | Phase 2 - Concept development |  |  |  | Killed | Major | Ongoing- Conclave- For GTF 1 Size developed, Balance when Needed, Drawings Are Ready.
25 | 1920FITTINGE19 | Test Stand Development | Fittings | Camozy Push in fittings/Exports Enquiry | Need to See the details- Competitors Products vs Our scope to define | bu #2 | Semi-Conductor | NA | NA | Minor Change | Nitin Patil | Gold | Nitin Patil | 2022-12-31 |  | Phase 0 |  |  |  | In-Process | Customer Specific | On Hold
26 | 1920FITTINGE20 | Test Stand Development | Fittings | Stortz Coupling | Need to See the details- Competitors Products vs Our scope to define. HIP, Butec | bu #1 | Semi-Conductor | NA | NA | Major Change | Nitin Patil | Gold | Not Assigned | When Needed | - | Phase 1 - Definition |  |  |  | Killed | Customer Specific | On Hold
27 | 1920FITTINGE21 | Test Stand Development | Fittings | Fittings For Aerospace Application | As per AS18280 & Boeing Part Details | bu #2 | Semi-Conductor | NA | NA | Complete New Product | Nitin Patil | Diamond | Pravin P | 2021-08-01 | 2023-12-31 | Phase 3 - Detail design |  |  |  | On-Hold | Major | Done- JJG ,AZAD
28 | 1920FITTINGE23 | Test Stand Development | Fittings | FCPL Crimping Machine- Single Ferrule Fitting | Buy & Self Development Model Suitable, Dies for sizes. Vass vs Stauff? Technical Catalogue is clear now to Buy. | bu #1 | Semi-Conductor | NA | NA | Minor Change | Krishna Rashtrakut | Platinum | Atul | 2019-12-01 | 2023-09-30 | Phase 1 - Definition |  |  |  | Killed | Done | Done-Machine Developed, Dies Development going on for Alstom Sizes
29 | 1920FITTINGE24 | Test Stand Development | Fittings | Double Ferrule Fittings Re-Enginnering | Issues Arise at Customer End, In-house, Validation of Products at its full rated capacity. Size 12 & Size 16 under trial. | bu #2 | Semi-Conductor | Exports | NA | Minor Change | Vinod Ghatge | Platinum | Pravin P | 2021-07-19 | 2023-09-30 | Phase 4 - Validation |  |  |  | In-Process | Major | Done- FEA Module 1 st Alt done, But Metallurgy defined and submitted Customer
30 | 1920VALVE01 | Product Development | Valve | Metal Seated ball valve For Hook-ups | Floating Type : 1/2" - 2" 6000 PSI- Fire Safe Type | bu #1 | Govt Railways - Loco | FCPL | NA | Complete New Product | Vinod Ghatge | Bronze | Santosh K | When Needed | - | Phase 1 - Definition |  |  |  | In-Process | Major | On hold Drawing Made, Validation Pending
31 | 1920VALVE15 | Product Development | Valve | Double Check Valve 3/4" BSP | As per Faiveley Drawing-A30020005 | bu #2 | Govt Railways - Loco |  | NA | Minor Change | Vinod Ghatge | Gold | Santosh K | When Needed | - | Phase 5 - Production |  |  |  | In-Process | Customer Specific | On Hold
32 | 1920VALVE16 | Product Development | Valve | Double Check Valve 3/8 Inch | As per Faiveley Drawing A4 002 0610 | bu #1 | Govt Railways - Loco |  | NA | Minor Change | Vinod Ghatge | Gold | Santosh K | When Needed | - | Phase 3 - Detail design |  |  |  | In-Process | Customer Specific | On Hold
33 | 1920VALVE17 | Product Development | Valve | Latched Isolating Cock 1-1/4" NON VENTED | As per Fevely Drawing | bu #2 | Govt Railways - Loco |  | NA | Minor Change | Praveen Patil | Diamond | Santosh K | 2021-12-02 | - | Phase 1 - Definition |  |  |  | Killed | Customer Specific | Done
34 | 1920VALVE18 | Product Development | Valve | Latched Isolating Cock 1-1/4" VENTED | As per Fevely Drawing | bu #1 | Govt Railways - Loco |  | NA | Complete New Product | Vinod Ghatge | Gold | Santosh K | 2021-12-02 | - | Phase 2 - Concept development |  |  |  | On-Hold | Customer Specific | Done
35 | 1920VALVE19 | Product Development | Valve | Angle Cock Valve RH (Globe Type) Size 3/4" Soft Seated, 3/4 Metal Seated", 1"Soft Seated & 1" Metal Seated | As per Faiveley Sample/Knorr received. FCPL Mfg. Cost & Investment, RDSO Approval Needed Yes/No | bu #2 | Govt Railways - Loco |  | NA | Complete New Product | Nitin Patil | Gold | Santosh K | On Demand | - | Phase 2 - Concept development |  |  |  | In-Process | Customer Specific | Inhouse costing Vs BO costing details for metal seated design are shared with Tansen sir on 30/07/2019. Decision awaited Sample/Component drawings required
36 | 1920VALVE20 | Product Development | Valve | Angle Cock Valve LH (Globe Type) Size 3/4" Soft Seated, 3/4 Metal Seated", 1"Soft Seated & 1" Metal Seated | As per Faiveley Sample/Knorr received. FCPL Mfg. Cost & Investment, RDSO Approval Needed Yes/No. | bu #1 | Govt Railways - Loco |  | NA | Major Change | Vinod Ghatge | Diamond | Santosh K | On Demand | - | Phase 1 - Definition |  |  |  | In-Process | Customer Specific | Inhouse costing Vs BO costing details for metal seated valves are shared with Tansen sir on 30/07/2019. Decision awaited Sample/Component drawings required
37 | 1920VALVE21 | Product Development | Valve | Isolating Cock OLP 1-1/4" | As per Fevely Drawing | bu #2 | Govt Railways - Loco |  | NA | Major Change | Vinod Ghatge | Gold | Santosh K | 2020-12-10 | 2024-03-31 | Phase 5 - Production |  |  |  | On-Hold | Customer Specific | Done
38 | 1920VALVE22 | Product Development | Valve | Isolating Cock CLP 1-1/4" | As per Fevely Drawing | bu #1 | Govt Railways - Loco |  | NA | Major Change | Praveen Patil | Platinum | Santosh K | 2020-12-10 | 2024-03-31 | Phase 2 - Concept development |  |  |  | Killed | Customer Specific | Done
39 | 1920VALVE23 | Product Development | Valve | Isolating Cock 1-1/4" VENTED | As per Fevely Drawing | bu #2 | Govt Railways - Loco |  | NA | Complete New Product | Nitin Patil | Bronze | Santosh K | 2020-12-10 | 2024-03-31 | Phase 4 - Validation |  |  |  | In-Process | Customer Specific | Done
40 | 1920VALVE25 | Product Development | Valve | 1", 1 1/4" CUT OFF ANGLE COCK WITH VENT (Floating ball valve) | As per Faiveley Drawing - 02 607 0475 | bu #1 | Govt Railways - Loco |  | NA | Major Change | Nitin Patil | Gold | Santosh K | 2020-12-10 | 2024-03-31 | Phase 2 - Concept development |  |  |  | Killed | Customer Specific | Done
41 | 1920VALVE26 | Product Development | Valve | Bellow seal valve-Cladding with colomony | New Product to be develop, with Compony cladding | bu #2 | Govt Railways - Loco |  | NA | Major Change | Praveen Patil | Gold | Santosh K | 2021-06-20 | - | Phase 1 - Definition |  |  |  | In-Process | On Hold | On Hold Cladding Process Sample to Be Prepare, Budgetary Offer submitted to Sales- Awaited Feedback.
42 | 1920VALVE28 | Product Development | Valve | DBB All Size | Design as per API 6D | bu #1 | Govt Railways - Loco | FCPL | NA | Minor Change | Praveen Patil | Platinum | Santosh K | 2020-12-01 | - | Phase 5 - Production |  |  |  | Killed | Major | On Hold- Drawing as per Inquiry done- No Order for Prototype
43 | 1920VALVE29 | Product Development | Valve | Check Valve (NRV) Spring Design | Select one size 1/2" NRV, Define Validation Parameter Cracking Pressure, Rate Pressure, Reliability how many cycles, Relatability with respect to change in spring | bu #2 | Govt Railways - Loco | FCPL | NA | Major Change | Vinod Ghatge | Gold | Santosh K | 2021-07-30 | - | Phase 5 - Production |  |  |  | Killed | Done | Done
44 | 1920VALVE31 | Product Development | Valve | Ball Valve Redesign Per Hydac | As per Hydac-1/4"to 2" | bu #1 | Govt Railways - Loco | FCPL | NA | Major Change | Nitin Patil | Gold | Santosh K | When Needed | - | Phase 3 - Detail design |  |  |  | On-Hold | Customer Specific | On Hold
45 | 1920VALVE32 | Product Development | Valve | Wallform- Hydac | As per Customer Drawings | bu #2 | Govt Railways - Loco |  | NA | Major Change | Praveen Patil | Silver | Santosh K | When Needed | - | Phase 4 - Validation |  |  |  | In-Process | Customer Specific | On Hold
46 | 1920VALVE34 | Product Development | Valve | Actuator Mountings Globe Valve-NB 150 | Globe 150 with Actuation | bu #1 | Govt Railways - Loco |  | NA | Major Change | Nitin Patil | Platinum | Santosh K | 2020-06-01 | - | Phase 3 - Detail design |  |  |  | On-Hold | Customer Specific | On Hold
47 | 1920VALVE35 | Product Development | Valve | Railway Horn | We have received samples, Collect details, | bu #2 | Govt Railways - Loco |  | NA | Minor Change | Vinod Ghatge | Diamond | Santosh K | When Needed | NA | Phase 1 - Definition |  |  |  | Killed | Customer Specific | On Hold : Drawing Made Technical Clarification From Customer for Qualification Specification is needed.
48 | 1920VALVE36 | Product Development | Valve | Railway Angle cock valve | We have received samples, Collect details, | bu #1 | Govt Railways - Loco |  | NA | Complete New Product | Praveen Patil | Silver | Santosh K | When Needed | - | Phase 2 - Concept development |  |  |  | On-Hold | Customer Specific | On Hold- Since its Duplicate Enquiry per Above per Development No 25
49 | 1920VALVE37 | Product Development | Valve | Ball Valves-GE 41 line items | GE design | bu #2 | Govt Railways - Loco |  | NA | Complete New Product | Krishna Rashtrakut | Diamond | Santosh K | When Needed | - | Phase 0 |  |  |  | Killed | Customer Specific | On Hold- Discussed with GE for Provide more details, Now with FT/Wabtec team
50 | 1920VALVE38 | Product Development | Valve | Diaphragm Valves | Need to Build Databased from Supplier/ Product Specification/ Costing/ Match with Enquiries Received | bu #1 | Govt Railways - Loco | FCPL | NA | Complete New Product | Krishna Rashtrakut | Platinum | Santosh K | 2020-06-20 | - | Phase 0 |  |  |  | In-Process | Customer Specific | Done- This is to be BO we have created supplier list & its details.
51 | 1920VALVE39 | Product Development | Valve | Solenoid Valve | Need to Build Databased from Supplier/ Product Specification/ Costing/ Match with Enquiries Received | bu #2 | Govt Railways - Loco | FCPL | NA | Major Change | Krishna Rashtrakut | Gold | Santosh K | 2020-06-20 | - | Phase 0 |  |  |  | Killed | Customer Specific | Done- This is to be BO we have created supplier list & its details.
52 | 1920VALVE40 | Product Development | Valve | Butterfly valve | Need to Build Databased from Supplier/ Product Specification/ Costing/ Match with Enquiries Received | bu #1 | Govt Railways - Loco | FCPL | NA | Major Change | Vinod Ghatge | Silver | Santosh K | 2020-06-20 | - | Phase 3 - Detail design |  |  |  | Killed | Customer Specific | Done- This is to be BO we have created supplier list & its details.
53 | 1920VALVE41 | Product Development | Valve | Gate valve | Need to Build Databased from Supplier/ Product Specification/ Costing/ Match with Enquiries Received | bu #2 | Govt Railways - Loco | FCPL | NA | Minor Change | Vinod Ghatge | Platinum | Santosh K | 2019-05-01 | - | Phase 0 |  |  |  | In-Process | Customer Specific | Done- This is to be BO we have created supplier list & its details.
54 | 1920VALVE42 | Product Development | Valve | Differential Pressure Control valve(DPCV) | Concept Finalised & submitted to KBL for Approval. | bu #1 | Govt Railways - Loco |  | NA | Complete New Product | Vinod Ghatge | Silver | Not Assigned | When Needed | NA | Phase 1 - Definition |  |  |  | In-Process | Customer Specific | On Hold
55 | 1920VALVE43 | Product Development | Valve | Electrical Ball Valve DN7, DH15,DN25 | As per GE | bu #2 | Govt Railways - Loco |  | NA | Major Change | Praveen Patil | Bronze | Santosh K | 2022-04-01 | 2024-03-31 | Phase 1 - Definition |  |  |  | On-Hold | Customer Specific | On hold - Procurement going on switches
56 | 1920VALVE44 | Product Development | Valve | Actuated Ball Valve | Domestic Enquiry (Sumprimo) | bu #1 | Govt Railways - Loco |  | NA | Complete New Product | Krishna Rashtrakut | Gold | Santosh K | When Needed | - | Phase 0 |  |  |  | Killed | Customer Specific | On Hold- Submitted to Supremo Concept , Awaited clearance
57 | 1920VALVE45 | Product Development | Valve | CNG valve -TMBV 1/2", 3/8", 3/4" | Swagelok Types', Parker -Need to certify as per MNGL & Other Natural Gas Specification | bu #2 | Govt Railways - Loco |  | NA | Major Change | Nitin Patil | Diamond | Sushila J | 2020-06-04 | 2024-09-30 | Phase 4 - Validation |  |  |  | In-Process | Major | Ongoing- Three Sizes Developed as BO & Submitted to Customer through Sales for Validation. Internal testing and validation in process.
58 | 1920FITTINGE25 | Test Stand Development | Fittings | Single Ferrule Redesign- to Meet International Brand- Voss/Stauff/ Parker Equivalent | 35 MM & 28 MM Ferrules to be swaged without insert. (6,10,12,18,22 MM ) | bu #2 | Semi-Conductor | FCPL | NA | Minor Change | Krishna Rashtrakut | Silver | Krishna & Atul | 2021-07-21 | 2023-09-30 | Phase 5 - Production |  |  |  | On-Hold | Done | Done- SS Done for Sizes per Alstom, CS In under Validation Test
59 | 1020CLAMP01 | Product Development | Clamps | Clamps for Alstom | Develop clamps for Alstom | bu #1 | Govt Railways - Loco |  | NA | Major Change | Nitin Patil | Platinum | Sanket | When Needed | NA | Phase 1 - Definition |  |  |  | Killed | Major | Ongoing- New desine trial sample submitted to customer.
60 | 1020ALL01 |  | All | GA Drawing Standardisation, Fittings, Valves, Clamps | GA drawings | bu #2 |  | NA | NA | Minor Change | Krishna Rashtrakut | Bronze | Krishna | 2021-04-01 | 2025-04-30 | Phase 5 - Production |  |  |  | In-Process | Major | Ongoing- Make all PDF & Cad in to Solid works. This is ongoing with Students Projects- Student need to allot for project
61 | 102HOSE01 | Product Development | Hoses | Indian Railway Hoses Development-CLW | As per Customer Drg | bu #1 | Govt Railways - Loco |  | NA | Complete New Product | Praveen Patil | Gold | Nitin P | 2021-04-01 | 2023-12-31 | Phase 0 |  |  |  | Killed | Major | Done-Drawing & Technical Review completed STR & Specification confirm with customer. Sample submitted.
62 | 1920VALVE60 | Product Development | Valve | Legris Type Valve - Define Fatigue Life (Operation life)- Target 10 L Cycles | As Customer Requirements | bu #2 | Govt Railways - Loco |  | NA | Minor Change | Vinod Ghatge | Platinum | Santosh K | 2019-03-01 | 2023-12-31 | Phase 0 |  |  |  | Killed | Customer Specific | Done.
63 | 1920VALVE61 | Product Development | Valve | ISOLATING COCK R1" WITHOUT VENT | As per Escorts drawing-3KB 167 -- | bu #1 | Govt Railways - Loco |  | NA | Major Change | Krishna Rashtrakut | Bronze | Santosh K | 2021-04-01 | NA | Phase 3 - Detail design |  |  |  | In-Process | Customer Specific | Done
64 | 1920VALVE62 | Product Development | Valve | THREE WAY COCK 1.1/2" (90 DEG MOVEMENT)- Brass. | As per Escorts drawing-3KB 572 | bu #2 | Govt Railways - Loco |  | NA | Complete New Product | Krishna Rashtrakut | Silver | Santosh K | 2021-01-04 | NA | Phase 5 - Production |  |  |  | On-Hold | Customer Specific | Done
65 | 1920VALVE64 | Product Development | Valve | GE Versa Valve | Design Approval form GE and Sample validation per GE specification | bu #1 | Govt Railways - Loco |  | NA | Complete New Product | Vinod Ghatge | Silver | Not Assigned | 2019-11-01 | - | Phase 2 - Concept development |  |  |  | On-Hold | Done | On Hold- Desing & Validation Done, Awating Customer Approval.
66 | 1920VALVE66 | Product Development | Valve | Legris Sheet Type A & B -21 line items in Brass & CS | Smaple for Exibition | bu #2 | Govt Railways - Loco | Sales | NA | Major Change | Krishna Rashtrakut | Gold | Santosh K | 2019-03-01 | 2023-12-31 | Phase 4 - Validation |  |  |  | On-Hold | Major | Ongoing- Need to develop Samples for CS
67 | 2021FITTINGE25 | Test Stand Development | Fittings | Hydro Fittings : Ratary For Bharat Forge | As per Parker to develop | bu #1 | Semi-Conductor | Domestci SMS/Metso/Distributor | NA | Major Change | Nitin Patil | Bronze | Krishna | 2022-03-31 | 2025-03-30 | Phase 4 - Validation |  |  |  | Killed | Major | Ongoing-3 Types developed addation 3 under development- Validation pending.
68 | 1920FITTINGE26 | Test Stand Development | Fittings | Hydro Fittings : CS Benjo Fittings & SW Fittings | As per Parker to develop | bu #2 | Semi-Conductor | Domestci SMS/Metso/Distributor | NA | Minor Change | Vinod Ghatge | Platinum | Krishna | 2021-12-01 | 2023-09-30 | Phase 4 - Validation |  |  |  | In-Process | Major | Done for As asked size- Need to Print Catlouge
69 | 1920FITTINGE27 | Test Stand Development | Fittings | Hydro Fittings : EO2/FCPL ES -Local Design Without Bonding | As per Parker to develop | bu #1 | Semi-Conductor | Domestci SMS/Metso/Distributor | NA | Minor Change | Krishna Rashtrakut | Bronze | Krishna | 2021-12-01 | 2023-05-30 | Phase 3 - Detail design |  |  |  | In-Process | Major | Done
70 | 1920FITTINGE27 | Test Stand Development | Fittings | Vent Fittings- Camron | As per Global Part Coade (P) & as per referance sample | bu #2 | Semi-Conductor | Domestci SMS/Metso/Distributor | NA | Complete New Product | Praveen Patil | Diamond | Krishna | 2022-03-22 | - | Phase 5 - Production |  |  |  | In-Process | Done | On Hold- Costing submiited awating Customer feedback
71 | 22-23FITTINGE28 | Test Stand Development | Fittings | Domestic Fittings 24 Deg to 37 Deg Cone Fittings | As per Parker | bu #1 | Semi-Conductor | Domestci SMS/Metso/Distributor | NA | Complete New Product | Krishna Rashtrakut | Silver | Krishna | When Needed | - | Phase 2 - Concept development |  |  |  | On-Hold | Done | Ongoing
72 | 22-23FITTINGE29 | Test Stand Development | Fittings | Domestic Fittings Minimise Coupler | As per Parker | bu #2 | Semi-Conductor |  | NA | Major Change | Vinod Ghatge | Silver | Krishna | When Needed | - | Phase 1 - Definition |  |  |  | In-Process | Customer Specific | on hold
73 | 22-23FITTINGE30 | Test Stand Development | Fittings | Alstom -Extr Long Connector- Perth Project | As per AT Drawing | bu #1 | Semi-Conductor |  | NA | Complete New Product | Vinod Ghatge | Platinum | Krishna | 2022-04-01 | 2022-10-10 | Phase 4 - Validation |  |  |  | Killed | Major | Done
74 | 1920VALVE67 | Product Development | Valve | Sigma Valve | Smaple Drawing and costing submitted to Sales Awating feedback | bu #2 | Govt Railways - Loco | Sales | NA | Minor Change | Praveen Patil | Bronze | Santosh K | 2012-01-01 | - | Phase 4 - Validation |  |  |  | Killed | Major | On Hold- Drawing & Costing Submitted awating Sales Feedback
75 | 2022ALL02 |  | All | Railway Break Component | Re-engineering of Components C3W Valve FT, KB List as per Break System | bu #1 |  | NA | NA | Minor Change | Vinod Ghatge | Platinum | Rahul P | 2021-04-01 | 2024-09-30 | Phase 2 - Concept development |  |  |  | Killed | Major | Need to conduct meeting for review scope
76 | 1920FITTINGE04 | Test Stand Development | Fittings | Fittings EO2- Domestic Market O ring seprate on Ferrule | Under validation 6 MM to 42 in L 12,18,28,22 Sample is ready & validated, Sereis S -16,06,10 MM taken for validation | bu #2 | Semi-Conductor | Sales | NA | Complete New Product | Nitin Patil | Gold | Krishna | 2022-10-15 | 2025-03-30 | Phase 2 - Concept development |  |  |  | Killed | Major | Ongoing- To do Burst Test for Validation
77 | 2122FITTING10 | Test Stand Development | Fittings | Alstom Cable Gland | As per Sample | bu #1 | Semi-Conductor |  | NA | Major Change | Praveen Patil | Silver | Krishna | 2022-12-31 | 2025-02-28 | Phase 5 - Production |  |  |  | Killed | Major | Ongoing -Costing submiited awating Customer feedback ,Need to Provide COC, Certification required.
78 | 2122FITTING12 | Test Stand Development | Fittings | Stauff Tube Flaring/OLAB Fititngs | As per Sample | bu #2 | Semi-Conductor |  | NA | Minor Change | Vinod Ghatge | Bronze | Krishna | When Needed | - | Phase 5 - Production |  |  |  | In-Process | Major | On Hold
79 | 2122FITTING13 |  |  | Rexel Coimbtoor -34 Parts |  | bu #1 |  |  |  | Major Change | Vinod Ghatge | Diamond |  |  |  | Phase 0 |  |  |  | In-Process
80 | 2122FITTING14 | Test Stand Development | Fittings | CNG Fititnngs Maruti Suzuki | As per Sample | bu #2 | Semi-Conductor |  | NA | Minor Change | Krishna Rashtrakut | Bronze | Pravin P | 2022-12-31 | 2023-09-30 | Phase 5 - Production |  |  |  | On-Hold | Major | Drawing and sample completed. Sample submitted to customer for FAI. Customer feedback awaited.
81 | 2122FITTING15 | Test Stand Development | Fittings | Oliver /MHA Zancraft Ball Valve Fittings- H2 Service We need to develop it | As per Customer Drawings | bu#1 | Semi-Conductor | Exports | NA | Minor Change | Praveen Patil | Diamond | Krishna | 2022-12-31 | 2023-09-30 | Phase 4 - Validation |  |  |  | Killed | Major | Done- Feed back awaited from customer
82 | 2122CERT01 | Product Certification | Certification | ABMS | System Certification |  | Oil & Gas | FCPL | NA | Complete New Product | Vinod Ghatge | Silver | Ramalal | 2022-08-01 | - | Phase 0 |  |  |  | On-Hold | Major | Completed
83 | 2122CERT02 | Product Certification | Certification | Welding Qualification- EN15085 | System Certification |  | Oil & Gas |  | NA | Major Change | Nitin Patil | Bronze | Ramalal | 2022-12-01 | 2024-09-30 | Phase 5 - Production |  |  |  | Killed | Major | On Going
84 | 2122CERT03 | Product Certification | Certification | ASME NPT | Product Certification |  | Oil & Gas | Oil & Gas, CNG | NA | Minor Change | Vinod Ghatge | Bronze | Ramalal | 2022-12-01 | 2024-09-30 | Phase 5 - Production |  |  |  | Killed | Major | Ongoing
85 | 2122CERT04 | Product Certification | Certification | QPL Certification for AS Fititngs | Product Certification |  | Oil & Gas |  | NA | Complete New Product | Vinod Ghatge | Platinum | Ramalal | 2022-12-01 | 2024-09-30 | Phase 3 - Detail design |  |  |  | On-Hold | Major | Ongoing- Initial preparation started, Matrix completed
86 | 2122CERT05 | Product Certification | Certification | ABS Valve & Manifold Revalidation | Product Certification |  | Oil & Gas | Oil & Gas | NA | Complete New Product | Praveen Patil | Gold | Ramalal | 2022-12-01 | - | Phase 1 - Definition |  |  |  | On-Hold | Major | Done
87 | 2122FITTING16 | Test Stand Development | Fittings | H2 Service Fittings | New Development |  | Semi-Conductor | Oil & Gas | NA | Major Change | Nitin Patil | Gold | Krishna | 2022-12-01 | 2025-03-30 | Phase 1 - Definition |  |  |  | In-Process | Major | Ongoing- compitator sample procurement in process for reverse engineering
88 | 2122FITTING16 | Process Development | Services | Rotary/360 Deg Fittings | New Development |  | Aerospace | Defence | NA | Complete New Product | Praveen Patil | Silver | Krishna | 2022-12-01 | 2023-03-30 | Phase 5 - Production |  |  |  | On-Hold | Major | Done
89 | 2122SERVICES01 | Process Development | Services | Kirloskar Servo Mechnism | New Development- Re engineering |  | Aerospace | Defence | NA | Complete New Product | Vinod Ghatge | Gold | Nitin P | 2022-12-01 | 2024-03-31 | Phase 0 |  |  |  | On-Hold | Major | Done
90 | 2122SERVICES02 | Process Development | Services | Defence Project Armed Vhecle | New Development |  | Aerospace | Defence | NA | Complete New Product | Nitin Patil | Gold | Krishna | 2022-12-01 | 2025-03-30 | Phase 3 - Detail design |  |  |  | Killed | Major | Ongoing
91 | 2122SERVICES04 | Process Development | Services | Hose Fittings Development | New Development |  | Aerospace | Hose | NA | Minor Change | Nitin Patil | Gold | Nitin P | 2022-12-01 | 2023-12-31 | Phase 3 - Detail design |  |  |  | In-Process | Major | Ongoing- Regular fitting developed. New fitting requirement identified.
92 | 2223VALVE68 | Product Development | Valve | Throttle valve | Development of Throttal Valve- Design, Manufacturing and Testing |  | Govt Railways - Loco |  | NA | Major Change | Vinod Ghatge | Bronze | Santosh K, Dilip | 2023-02-26 | 2023-12-31 | Phase 3 - Detail design |  |  |  | On-Hold | Customer Specific | On hold- Drawing and Sample ready.
93 | 2223FITTING | Test Stand Development | Fittings | Quick Connector | New Development |  | Semi-Conductor |  | FCR49316 | Complete New Product | Nitin Patil | Bronze | Nitin P | 2022-10-21 | Done | Phase 1 - Definition |  |  |  | On-Hold | Major | Done- Sample submitted to customer. Need to type test at our lab.
94 | 2223fitting 01 | Test Stand Development | Fittings | Hinges development for Alstom | Alstom/ Rexel New development |  | Semi-Conductor |  | FCR49E0097 / 103 | Major Change | Vinod Ghatge | Diamond | Krishna | 2023-01-01 | - | Phase 4 - Validation |  |  |  | On-Hold | Major | Submitted to customer
95 | 2223FITTING02 | Test Stand Development | Fittings | Telescopic Rod | Alstom/ Rexel New development |  | Semi-Conductor |  | FCR49E0097 / 103 | Minor Change | Vinod Ghatge | Gold | Krishna | 2023-01-01 | - | Phase 5 - Production |  |  |  | In-Process | Major | requirement is closed, due to feasibility
96 | 2223FITTING03 | Test Stand Development | Fittings | Saftey Catch | Alstom/ Rexel New development |  | Semi-Conductor |  | FCR49E0097 / 103 | Complete New Product | Vinod Ghatge | Gold | Krishna | 2022-06-01 | 2024-09-30 | Phase 5 - Production |  |  |  | Killed | Major | Sample submitted to customer feedback awaited from customer. Customer end end validation going on.
97 | 2223FITTING03 | Test Stand Development | Fittings | 36 New parts development 11 Cable glands, 25 Cu, Al, CS materials | Alstom/ Rexel New development |  | Semi-Conductor |  | FCR49E0097 / 103 | Minor Change | Praveen Patil | Silver | Krishna | 2022-06-01 | 2025-01-30 | Phase 4 - Validation |  |  |  | In-Process | Major | 13 Parts developed 23 parts in process for development. 13 Parts submitted to customer for fitment. Customer will be share drawing for clearification of technical specification.
98 | 2223FITTING03 | Test Stand Development | Fittings | Hydrogen fittings - all sizes (06 Nos) | Export / Domestic |  | Semi-Conductor | Export / Domestic | NA | Minor Change | Vinod Ghatge | Gold | Krishna | 2023-01-01 | - | Phase 1 - Definition |  |  |  | Killed | Major | 12 mm size submitted to customer feedback awaited. Remaining sizes need to review.
99 | 2324VALVE01 | Product Development | Valve | Latching Cock- Ball valve | Development of Valve- Design, Manufacturing and Testing |  | Govt Railways - Loco |  | FCR50E0021 | Complete New Product | Vinod Ghatge | Silver | Santosh K | 2023-04-13 | 2023-06-03 | Phase 3 - Detail design |  |  |  | In-Process | Customer Specific | Done- Sample submitted to customer
100 | 2324VALVE02 | Product Development | Valve | Latching Cock- Casting handle bolted body | Development of Valve- Design, Manufacturing and Testing |  | Govt Railways - Loco | Export | FCR49E0382 | Minor Change | Praveen Patil | Silver | Santosh K | When Needed | - | Phase 1 - Definition |  |  |  | In-Process | Customer Specific | Done
101 | 2324VALVE03 | Product Development | Valve | Check Valve- Self operating | Development of Valve- Design, Manufacturing and Testing |  | Govt Railways - Loco | Domestic | NA | Major Change | Praveen Patil | Gold | Santosh K | 2023-07-26 | 2023-12-31 | Phase 3 - Detail design |  |  |  | Killed | Customer Specific | On hold- Costing Submitted to sales, customer reply awaiting
102 | 2324SERVICE01 | Process Development | Services | Rotary Actuator | Deisgn and Manufacturing of Rotary Actator |  | Aerospace | Defence | NA | Minor Change | Krishna Rashtrakut | Diamond | Nitin P | 2023-03-31 | 2024-03-31 | Phase 3 - Detail design |  |  |  | On-Hold | DRDO | On going- Drawing Ready, Hold at customer end
103 | 2324PROCESS01 | Process Development | Process | KBF Altenative | Development new process |  | Aerospace | FCPL | NA | Major Change | Nitin Patil | Platinum | Jeet Shaha | 2022-10-12 | 2024-05-15 | Phase 2 - Concept development |  |  |  | In-Process | Major | On going- 2 Trials conducted, PIN process development going on. CNG ferrule trial going on. Electrocleaning trial in process. 3/4 and 1" Completed
104 | 2324PROCESS02 | Process Development | Process | Vaccum Annealing Chamber Specification to design | Development design and manufacturing |  | Aerospace | FCPl | NA | Complete New Product | Nitin Patil | Platinum | Jeet Shaha | 2023-07-30 | 2024-09-30 | Phase 2 - Concept development |  |  |  | Killed | Major | On going- supplier Quotation taken.
105 | 2324CERT01 | Product Certification | Certification | NPCIL Fittings Approval | Product Certification |  | Oil & Gas | Nuclear | NA | Minor Change | Vinod Ghatge | Platinum | Jeet Shaha | 2022-12-01 | 2024-09-30 | Phase 2 - Concept development |  |  |  | On-Hold | Major | On going- Discussion in process with customer
106 | 2324FITTING01 | Product Development | Special Project | CADNAS | Website upgradation |  | Govt Railways - Loco |  |  | Complete New Product | Praveen Patil | Gold | Krishna | 2023-03-31 | - | Phase 3 - Detail design |  |  |  | Killed | Major | Ongoing- 1st stage -79 Itemes completed.
107 | 2324 |  | System | All System Upgradation | All design system need to update |  |  |  | NA | Complete New Product | Nitin Patil | Gold | Snaket Patil | 2023-03-31 | 2023-10-30 | Phase 2 - Concept development |  |  |  | In-Process | Major | Done
108 | 2324SERVICE02 | Process Development | Services | Sample Probe | Development - Manufacturing and Testing |  | Aerospace |  | NA | Complete New Product | Praveen Patil | Gold | Abhay Dake,Mahesh Kekane, Ramalal | 2023-05-30 | 2024-03-31 | Phase 1 - Definition |  |  |  | In-Process | Major | On Hold- Quotation submitted to customer
109 | 2324TESTING01 | Test Stand Development | Testing | High Temp/Low Temprature Pressure Impulse Test Setup | Development- Design, Manufacturing and Testing |  | Semi-Conductor | Hose , Tube Fitting | NA | Minor Change | Praveen Patil | Bronze | Ganehs L/Mahehs K | 2023-04-30 | 2023-09-30 | Phase 1 - Definition |  |  |  | On-Hold | Major | Done- Testbench completed trial conducted, System upgradation. Customer Testing started
110 | 2324 |  |  | Patents | [5 empty] | Minor Change | Praveen Patil | Silver | All, Rahul Patil |  |  | Phase 1 - Definition |  |  |  | On-Hold |  | On going
111 | 2324SP01 | Product Development | Special Project | Surface Tretment Process | Development new process |  | Govt Railways - Loco | Aerospace | NA | Complete New Product | Vinod Ghatge | Silver | Rahul Patil | 2023-07-25 | 2024-09-30 | Phase 2 - Concept development |  |  |  | On-Hold | Major | On going- Drawing Ready, Sample preparation started
112 | 2324SP01 | Product Development | Special Project | Flag Rod Assembly | Development new process |  | Govt Railways - Loco |  | NA | Major Change | Vinod Ghatge | Platinum | Nitin Patil | 2023-06-01 | 2024-09-30 | Phase 3 - Detail design |  |  |  | In-Process | Major | On going- Drawing Ready, Sample preparation started. Sample testing completed PO received for sample development. Dies development in process
113 | 2324SP02 | Product Development | Special Project | Flag Rod Assembly-(6mm OD Size assly) | Development new process |  | Govt Railways - Loco |  | NA | Major Change | Nitin Patil | Diamond | Nitin Patil | 2023-08-30 | 2024-09-30 | Phase 2 - Concept development |  |  |  | On-Hold | Major | On going- Drawing Ready, Sample preparation started. Sample testing completed PO received for sample development. Parts submitted to custome. Feedback awaited
114 | 2324SP03 | Product Development | Special Project | Manifold Assembly | Development new process |  | Govt Railways - Loco |  | NA | Complete New Product | Nitin Patil | Platinum | Nitin Patil | 2023-08-30 | 2023-11-30 | Phase 4 - Validation |  |  |  | On-Hold | Major | On going- Drawing Ready, Sample preparation started. Sample testing completed PO received for sample development. Under quotation review stage.
115 | 2324SP04 | Product Development | Special Project | Hydraulic Lift-Testing | Development- Testing Rig for Hydraulic lift |  | Govt Railways - Loco | Defence | NA | Minor Change | Praveen Patil | Platinum | Nitin Patil | 2023-08-30 | 2023-12-31 | Phase 5 - Production |  |  |  | In-Process | Major | Onging- Quotation submit to Customer
116 | 2324SP05 | Product Development | Special Project | Eo2 Form Fitting development | Development of sizes 10,12,18mm |  | Govt Railways - Loco | Defence/ Railway | NA | Major Change | Praveen Patil | Diamond | Nitin Patil | 2023-10-01 | 2024-09-30 | Phase 0 |  |  |  | Killed | Major | Ongoing- Machine under procurment.
117 | 2324SP06 | Product Development | Special Project | Eo2 Fitting & Ferrule development | Development of sizes 06,08,10,12mm |  | Govt Railways - Loco | Defence/ Railway | NA | Minor Change | Praveen Patil | Gold | Nitin Patil | 2023-10-01 | 2024-09-30 | Phase 4 - Validation |  |  |  | In-Process | Major | Ongoing- Compititor sample procurement going on. Drawing completed and sample submitted to customer. (tube size 6 and 8 mm completed)
118 | 2324VALVE04 | Product Development | Valve | Safety Relief Valve For CNG From Parker Sample | Development of Valve- Design, Manufacturing and Testing |  | Govt Railways - Loco | Domestic | NA | Complete New Product | Vinod Ghatge | Bronze | Vinod G,Sushila J | 2023-11-07 | 2023-12-31 | Phase 5 - Production |  |  |  | In-Process | Major | Done- Need to develop Samples in SS (Brought out from supplier)
119 | 2324VALVE05 | Product Development | Valve | Ball Valve For CNG From Parker Sample | Development of Valve- Design, Manufacturing and Testing |  | Govt Railways - Loco | Domestic | NA | Major Change | Krishna Rashtrakut | Silver | Vinod G,Sushila J | 2023-11-07 | - | Phase 4 - Validation |  |  |  | Killed | Major | Ongoing- Design ready , Sample preparation in process.
120 | 2324TESTING02 |  | Testing | Enhancement of Pneumatic testing | Development- Design, Manufacturing and Testing |  |  | Hose , Tube Fitting | NA | Major Change | Nitin Patil | Platinum | Ganehs L/Mahehs K | 2023-10-01 | 2023-11-30 | Phase 5 - Production |  |  |  | On-Hold | Major | Done- Testbench completed trial conducted, System upgradation. Customer Testing started
121 | 2324TESTING03 |  | Testing | Heat decipation and pressure drop testing | Development- Design, Manufacturing and Testing |  |  |  | FC501274 | Minor Change | Nitin Patil | Platinum | Ganehs L/Mahehs K | 2023-08-01 | 2023-12-31 | Phase 3 - Detail design |  |  |  | In-Process | Customer Specific | Done- T+A111:L123estbench completed trial conducted, System upgradation. Customer Testing started
122 | 2324TESTING04 | Test Stand Development | Testing | Fire Testing EN45545 | Development- Design, Manufacturing and Testing |  | Semi-Conductor | Hose and Tube Testing | NA | Minor Change | Praveen Patil | Silver | Ganehs L/Mahehs K | 01/10/203 | 2024-09-30 | Phase 3 - Detail design |  |  |  | Killed | Major | Ongoing- Drawing submitted to supplier. Manufacturing started
123 | 2324SP07 | Product Development | Special Project | Tata Advance | Kit1,2,3,4 Tube & Hose Assemblies LHD and RHD |  | Govt Railways - Loco | Defence | NA | Minor Change | Nitin Patil | Gold | Nitin Patil | 2023-10-01 | 2024-03-31 | Phase 0 |  |  |  | On-Hold | Major | On Hold
124 | 2324SP08 | Product Development | Special Project | Trafo Oil Tube assemblies | 2 types of Welded tube assemblies of 88 mm bend tubes |  | Govt Railways - Loco | Railways | NA | Complete New Product | Nitin Patil | Silver | Nitin Patil | 2023-10-01 | 2024-03-31 | Phase 3 - Detail design |  |  |  | On-Hold | Major | Ongoing- Child part received. Welding trail going on.
125 | 2324SP09 | Product Development | Special Project | Special Tube bending Tool Development | Special purpose bending tool development critical bending of 10mm od tube for wabtech |  | Govt Railways - Loco | Railways | NA | Major Change | Krishna Rashtrakut | Bronze | Nitin Patil | 2023-10-01 | 2024-03-31 | Phase 2 - Concept development |  |  |  | Killed | Major | 10 mm tool developed. 6 mm in process
126 | 2324SP10 | Product Development | Special Project | Aerospace bending development | Bending of 31.75X0.711 thk,50.8X0.889 thk,19.05X0.991 thk |  | Govt Railways - Loco | Aerospace | NA | Minor Change | Vinod Ghatge | Gold | Nitin Patil | 2023-12-01 | 2024-03-31 | Phase 2 - Concept development |  |  |  | Killed | Major | New bending machine/special bending tool
127 | 2324SERVICE03 | Process Development | Services | Analysis (FEA/CFD) | FEA and CFD of Shelter |  | Aerospace |  | NA | Major Change | Vinod Ghatge | Bronze | Ganehs Lohar | 2023-12-25 | 2024-03-31 | Phase 4 - Validation |  |  |  | Killed | Major | 19 Models completed.
128 | 2324SERVICE04 | Process Development | Services | Leak Testing | Air Pressure testing of Ships |  | Aerospace |  | NA | Major Change | Vinod Ghatge | Diamond | Ganesh L/ Mahesh K | 2023-12-25 | 2024-09-30 | Phase 3 - Detail design |  |  |  | Killed | Major | Quotation share.
129 | 2324VALVE06 | Product Development | Valve | Development of 20K PSI Needle Valve- Design, Manufacturing and Testing as per API6A (PR2F qualification) | Development- Design, Manufacturing and Testing |  | Govt Railways - Loco |  | FCEX50E0168 | Complete New Product | Krishna Rashtrakut | Gold | Vinod G, Santosh K, Dilip | 2023-11-02 | 2024-09-30 | Phase 1 - Definition |  |  |  | On-Hold | Customer Specific | On going- Design completed. Sample Manufacturing going on. Testinf setup in process
130 | 2425VALVE01 | Product Development | Valve | 1", 1 1/4" CUT OFF ANGLE COCK WITH VENT (Floating ball valve) | As per Faiveley/Knoor Bremse- Design, Manufacturing and Testing |  | Govt Railways - Loco |  | NA | Complete New Product | Vinod Ghatge | Platinum | Santosh K, Sushila J | 2024-04-13 | 2024-09-30 | Phase 4 - Validation |  |  |  | In-Process | Customer Specific | On going- Design in process
131 | 2425VALVE02 | Product Development | Valve | Ball Valve and Check Valve | Development- Design, Manufacturing and Testing |  | Govt Railways - Loco |  | FC50E1647 | Major Change | Praveen Patil | Diamond | Santosh K | 2024-04-05 | 2024-09-30 | Phase 0 |  |  |  | In-Process | Customer Specific | Project will be start after reciept of sample.
132 | 2324FITTING02 | Test Stand Development | Fittings | Coupling Sleeve,Plug and Cap | Development- Design, Manufacturing and Testing |  | Semi-Conductor |  | FCEX50E0021 | Major Change | Krishna Rashtrakut | Platinum | Fija B | 2023-05-05 | 2024-09-30 | Phase 4 - Validation |  |  |  | In-Process | Customer specific | On going- Quotation approved by customer, Sample in process
133 | 2324AERO01 | Test Stand Development | fittings | Hydraulic Fitting | Drawing, Manufacturing and Testing |  | Semi-Conductor |  | FC50E1129 | Minor Change | Nitin Patil | Gold | Fija B | 2023-11-02 | 2024-09-30 | Phase 5 - Production |  |  |  | On-Hold | Major | On going- Quotation submitted to customer, QPL programm in process
134 | 2324SP11 | Product Development | Special Project | Hydraulic Cylinder- 4 Types | Development - Manufacturing and Testing |  | Govt Railways - Loco | Oil and Gas | NA | Major Change | Nitin Patil | Silver | Suyog B | 2024-03-15 | - | Phase 5 - Production |  |  |  | On-Hold | Major | Catlogue in process
135 | 2324SP12 | Product Development | Special Project | Canister Luncher-3 Types | Development - Manufacturing and Testing |  | Govt Railways - Loco | Aerospace | FC50E1622 | Complete New Product | Praveen Patil | Bronze | Suyog B | 2024-01-27 | 2024-09-30 | Phase 1 - Definition |  |  |  | In-Process | Major | Costing submitted to custmer.
136 | 2324SP13 | Product Development | Special Project | Fuel Pump | Development - Manufacturing and Testing |  | Govt Railways - Loco | Aerospace | FC50E1886 | Complete New Product | Nitin Patil | Gold | Suyog B | 2024-03-01 | 2024-09-30 | Phase 3 - Detail design |  |  |  | Killed | Major | Costing submitted to custmer.
137 | 2324SP14 | Product Development | Special Project | Tube Bending - conduit | Development - Manufacturing and Testing |  | Govt Railways - Loco |  | FC50E1600 | Minor Change | Vinod Ghatge | Silver | Suyog B, Sanket P | 2024-02-09 | 2024-09-30 | Phase 0 |  |  |  | In-Process | Major | Done
138 | 2324SP15 | Product Development | Special Project | SKID (Fibrication) | Development - Manufacturing |  | Govt Railways - Loco |  | FC50E1600A | Complete New Product | Vinod Ghatge | Diamond | Suyog B | 2024-06-17 | 2025-05-15 | Phase 2 - Concept development |  |  |  | In-Process | Major | Done
139 | 2324SP16 | Product Development | Special Project | HYDRAULIC & PNEUMATIC CIRCUIT PANEL (MPHPC) | Development - Manufacturing and Testing |  | Govt Railways - Loco |  | FC51E1474 | Minor Change | Praveen Patil | Gold | Suyog B, Ganesh L | 2024-09-06 | 25-03-024 | Phase 3 - Detail design |  |  |  | Killed | Major | Done
140 | 2324SP17 | Product Development | Special Project | CDR BOX -2 (Fibrication) | Development - Manufacturing |  | Govt Railways - Loco |  | FC51E2021 | Major Change | Krishna Rashtrakut | Diamond | Suyog B | 2025-03-13 | - | Phase 0 |  |  |  | On-Hold | Major | Costing submitted to custmer.
141 | 2324SP18 | Product Development | Special Project | Central Tool Room & Training Centre (CTDC) Bhuvaneswar | Development - Manufacturing and Testing |  | Govt Railways - Loco |  | - | Minor Change | Krishna Rashtrakut | Diamond | Suyog B | 2025-03-10 | - | Phase 4 - Validation |  |  |  | On-Hold | Customer Specific | Costing submitted to custmer.
142 | 2324SP19 | Product Development | Special Project | CDR BOX -1 (Fibrication) | Development - Manufacturing |  | Govt Railways - Loco |  | FC51E1338 | Complete New Product | Krishna Rashtrakut | Diamond | Suyog B | 2024-11-05 | - | Phase 0 |  |  |  | On-Hold | Major | Costing submitted to custmer.
143 | 2324SP20 | Product Development | Special Project | REFRIGERANT TUBES BULKHEAD ASSY. | Development - Manufacturing and Testing |  | Govt Railways - Loco |  | FC51E2090 | Complete New Product | Vinod Ghatge | Diamond | Suyog B | 2025-03-31 | 2025-03-08 | Phase 5 - Production |  |  |  | Killed | Customer Specific | Costing submitted to custmer.
138 | 2425HOSE01 |  | Hoses | Fire saftey hose and fittings | Development - Manufacturing and Testing |  |  |  |  | Major Change | Krishna Rashtrakut | Silver | Nitin P | 2024-04-15 | 2024-09-30 | Phase 3 - Detail design |  |  |  | On-Hold | Customer Specific | Design in process
139 | 2425TUBE01 |  | Tube | Bend Tube | Development - Manufacturing and Testing |  |  |  | FC50E1574 | Minor Change | Vinod Ghatge | Gold | Nitin P | 2024-04-10 | 2024-09-30 | Phase 5 - Production |  |  |  | In-Process | Customer Specific | Design in Process
140 | 2425SP01 | Product Development | Special Project | SS hose assembly Welding | Development - Manufacturing and Testing |  | Govt Railways - Loco | New product | NA | Minor Change | Nitin Patil | Platinum | Nitin P | 2024-04-15 | 2024-09-30 | Phase 5 - Production |  |  |  | On-Hold | Major | Scope identification in process
141 | 2425SP02 | Product Development | Special Project | Water Mist Nozzle | Development - Manufacturing analysis and Testing |  | Govt Railways - Loco |  | FC50E1450 | Minor Change | Nitin Patil | Platinum | Suyog B, Sanket P, Ganesh L | 2024-04-01 | 2024-09-30 | Phase 3 - Detail design |  |  |  | In-Process | Customer Specific | Quoatation submitted to customer. Design ready. FEA in process
142 | 2324TESTING05 | Test Stand Development | Testing | High Pressure pulsation setup 1400 Bar fully automatic | Development- Design, Manufacturing and Testing |  | Semi-Conductor | Hose , Tube Fitting | NA | Complete New Product | Nitin Patil | Platinum | Ganesh L/ Mahesh K | 2024-01-01 | 2024-05-10 | Phase 0 |  |  |  | Killed | Major | Done
143 | 2324TESTING06 | Test Stand Development | Testing | PR2F- Tersting setup | Development- Design, Manufacturing and Testing |  | Semi-Conductor | Valve and fitting | NA | Major Change | Praveen Patil | Diamond | Ganesh L/ Mahesh K | 2024-03-25 | 2024-05-10 | Phase 2 - Concept development |  |  |  | Killed | Major | Done
144 | 2425TESTING01 | Test Stand Development | Testing | Enhancement of Manual Testing | Graphical representation of Testing |  | Semi-Conductor | Test Bench | NA | Major Change | Praveen Patil | Diamond | Ganesh L/ Mahesh K | 2024-04-10 | 2024-08-30 | Phase 5 - Production |  |  |  | Killed | Major | On going
145 | 2425SERVICE01 | Process Development | Services | FC fitting intermixability study with swagelok Fitting | Validation As per ASTM F1387 |  | Aerospace |  | NA | Complete New Product | Praveen Patil | Bronze | Ganesh L/ Mahesh K | 2024-04-01 | 2024-05-25 | Phase 4 - Validation |  |  |  | In-Process | Major | Done
146 | 2425CERT01 | Product Certification | Certification | Scope addition in NABL - Hose and Tube testing | All standard relevent with Hose and tube testing |  | Oil & Gas | All | NA | Complete New Product | Nitin Patil | Silver | Ganesh L/ Mahesh K | 2024-04-01 |  | Phase 5 - Production |  |  |  | On-Hold | Major | Standard and scope identification in process.
147 | 2425FITTING01 | Test Stand Development | Fittings | Fittings benchmark with swagelok | 5 Types of fitting re-engineering as per swageleok , Manufacturing and validation |  | Semi-Conductor |  | FC50E1625 | Minor Change | Praveen Patil | Bronze | Krushna R, Ganesh L, Atul K | 2024-04-01 | 2024-05-15 | Phase 2 - Concept development |  |  |  | In-Process | Major | Dimension, Drawing and manufacturing inprocess
148 | 2324AERO02 | Test Stand Development | fittings | Hydraulic Fitting, tube Brazing | Drawing, Manufacturing and Testing |  | Semi-Conductor |  | FC51E1395 | Major Change | Praveen Patil | Platinum | Fija B | 2024-11-05 | 2024-11-13 | Phase 5 - Production |  |  |  | In-Process | Major | PO Received, Samples Dispatched for approval
149 | 2324AERO03 | Test Stand Development | fittings | Hydraulic Fitting, tube Brazing | Drawing, Manufacturing and Testing |  | Semi-Conductor |  | FC51E1562 | Major Change | Krishna Rashtrakut | Bronze | Fija B | 2024-12-18 | 2024-12-26 | Phase 3 - Detail design |  |  |  | In-Process | Major | PO Received, Samples Dispatched for approval
150 | 2425AEROC01 | Process Development | Aerospace | AEROSPACE fuel line COUPLING FOR ADE | 6 TYPES OF COUPLING FITTING re-engineering as per Sample , Manufacturing and validation |  | Aerospace |  | FC51E1798/FC51E1737 | Major Change | Praveen Patil | Platinum | Sanket P. / Yedukar Sir | 2025-03-10 | 2025-05-10 | Phase 0 |  |  |  | In-Process | Major | Design in process
151 | 2425AEROF01 | Process Development | Aerospace | AEROSPACE FITTING (PERMASWAGE) FOR ADE | 6 TYPES OF FITTING re-engineering as per Sample (PERMASWAGE) , Manufacturing and validation |  | Aerospace |  | FC51E1738 | Major Change | Nitin Patil | Platinum | Sanket P. / Yedukar Sir |  |  | Phase 0 |  |  |  | On-Hold
152 | 2526VALVE01 | Product Development | Valve | NON-RETURN VALVE IN BRASS | Development- Design, Manufacturing and Testing as per sample. |  | Govt Railways - Loco |  | NA | Complete New Product | Vinod Ghatge | Diamond | Santosh K | 2025-04-05 | 2025-04-20 | Phase 5 - Production |  |  |  | In-Process | Customer Specific | On going
153 | 2526VALVE02 | Product Development | Valve | NON-RETURN VALVE IN SS316 | Development- Design, Manufacturing and Testing as per sample. |  | Govt Railways - Loco |  | NA | Complete New Product | Krishna Rashtrakut | Bronze | Santosh K | 2025-03-25 | 2025-04-30 | Phase 2 - Concept development |  |  |  | On-Hold | Customer Specific | On going

## Updates - Excel File
Sr.No. | Project Number (Earlier Development Number) | Project Category | Product Category (only for Product Development & Certification Projects) | Title of Project | High Level Scope Of Project | Business Unit | Market Segment | Lead Customer Name | Enquiry Number (if Applicable) | Project Risk Classification | Business Opportunity | Customer Specific Project? - Yes/No | Engineering Leader (Old Project Owner) | Project Leader | Planned Start Date | Target Completion Date | Project Phase | Actual Start Date | Forecast Completion Date | Actual Completion date | Overall Status | Remarks
|  | Product Development | Tube Fitting |  |  | BU #1 | Govt Railways - Loco |  |  | Minor Change | Bronze |  | Krishna Rashtrakut |  |  |  | Phase 0 |  |  |  | Completed
|  | Product Development | Hose Fitting |  |  | BU #1 | Govt Railways - Coaches |  |  | Major Change | Silver |  | Krishna Rashtrakut |  |  |  | Phase 1 - Definition |  |  |  | In-Process
|  | Product Development | Valve |  |  | BU #1 | Private Railways |  |  | Complete New Product | Gold |  | Krishna Rashtrakut |  |  |  | Phase 2 - Concept development |  |  |  | On-Hold
|  | Product Development | Clamp |  |  | BU #1 | Oil & Gas, Down/Up Stream |  |  |  | Platinum |  | Krishna Rashtrakut |  |  |  | Phase 3 - Detail design |  |  |  | Killed
|  |  | Tube Assembly |  |  | BU #1 | Industrial Application |  |  |  | Diamond | [5 empty] | Phase 4 - Validation
|  |  | Hose Assembly |  |  | BU #2 | Aerospace | [9 empty] | Phase 5 - Production
|  |  | Fabrication |  |  | BU #2 | Defence
[6 empty] | BU #2 | Semi-Conductor
[6 empty] | BU #2 | Testing & Engg Services

## Updates - Power Bi Dashboard
Power Bi Dashboard
Page 1 (Landing Page) |  | Overall Project demographics
Graph | 1 | Total Project Count | OK
Graph | 2 | Count of Project by Status | OK
Graph | 3 | Count of Project by Project Category | Add
Graph | 4 | Count of Project by Product Category | OK
Graph | 5 | Count of Project by Risk Classification | Add
Graph | 6 | Count of Project by Business Opportunity | Add
Graph | 7 | Count of project by Project Phase | Add
Graph | 8 | Count of project by Quarter | Remove ?
Drop Down Selection | 1 | Project Status | Required ? May be duplication
| 2 | Product Category | Required ? May be duplication
| 3 | Project Owner/Leader | Required?
| 4 | Date of Start | Required? Linked to Graph 8
| 5 | Business Unit | Add
| 6 | Market Segment | Add
| 7 | Customer | Add
Page 2 |  | Project Details
Required? May be duplication with Page 1
Page 3 |  | Resource Analysis
Graph | 1 | Count of Project by Engineering Leader
| 2 | Count of Project by Project Leader